## WBS
The project WBS activities:
No. | Activities | Estimate Duration | Activity Description
1 | Project proposal | 3 weeks | Write project proposal
2 | Research | 1 week | Find different sources and tools. Find similar open source applications which coud help to create the project
3 | Check the requiments nad specification | 1 week | List all the functions for the web application
4 | Design the back-end | 1 week | Design the backend using program for creating UML diagrams
5 | Desing the front-end | 1 week | Desing the front-end using Figma and/or Adobe Photoshop
6 | Interim Project Report | 2 weeks | Write Interim Porject Report
7 | Back-end prototype | 3 weeks | Develop all the functionality. Write the methods.
8 | Front-end prototype | 3 weeks | Develop all the components for front-end purpose.
9 | Add more functions | 1 weeks | If there is enaugh time add more features.
10 | Integerate back-end and front-end. | 1 week | Connect the frontend and backend togheather.
11 | Wite final report | 4 weeks | Produce final report
12 | Check final report |  | Correct any strcute or grammar issues
13 | Viva | 1 week | Prepare for demonstration the web applciation
| Total Duration: | 25 weeks

## Gantt Chart
Gantt Chart CLS
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25
Crew Logistic System
Inception Phase |  | 4 weeks
Research
Project Proposal and Project plan
Elaboration Phase | [6 empty] | 5 weeks
Analise Requiments and Specification
Back-end desing
Front-end design
Write interim Project Report
Construction Phase | [14 empty] | 10 weeks
Create the model and the database
Build back-end side
Build front-end side
Add more functions
Review the prototype and fucntionality
Integrate back-end and front-end sides
Test the application.
Transition Phase | [22 empty] | 6 weeks
Write final report
Check final report
Prepare for Viva
M1
M2
M3
M4
M5
M6